## Backlog
Sprint Backlog
***หมายเหตุ: กำหนดให้แต่ละ Sprint มีความยาว 1 สัปดาห์เท่ากัน |  |  | Group
Sprint No. | Product Backlog Items | Sprint Tasks | Initial Estimate of Effort | New Estimate of Effort Remaining at The End of Day…
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7
1 | As an alumnus, I want to purchase a souvenir so that I can contribute to the College of Computing. | Design and Edit Product Page | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0
|  | Design and Edit Product Detail Page | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0
|  | Design and Edit Cart Page | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0
|  | Design and Edit Payment Page | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0
|  | Add Module Paymant | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0
|  | Add Product To Website | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0
|  | Create Slide Presentation | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0
|  | Create user manual (For Admin) | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0
|  | Create user manual (For customer) | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0
|  | Test Manual UI Page (Product, Detail, Cart, Payment) | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0
|  | Create Test Document | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0
|  | Create Install guide | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0
|  | Create UAT Document | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0
|  | Design Product | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0
|  | Install Prestashop | 12 | 12 | 12 | 12 | 12 | 0 | 0 | 0
|  | Total | 86 | 71.6667 | 57.3333 | 43 | 28.6667 | 14.3333 | 0 | 0
2 | As a user, I want to switch language at all time. | Design Ui First page | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
|  | Design Ui Second page | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
|  | Design Ui Thirt page | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
|  | User Manual | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0
|  | Theme Language Module | 6 | 6 | 6 | 6 | 6 | 0 | 0 | 0
|  | Test Script | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0
|  | Prepare Data (TH EN ID) | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0
|  | Sprint backlog + Burndownchart | 6 | 6 | 6 | 6 | 6 | 6 | 0 | 0
|  | ADAPT_BP | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0
|  | Total | 35 | 29.1667 | 23.3333 | 17.5 | 11.6667 | 5.8333 | 0 | 0
3 | As a user, I want to switch language at all time. | User Manual For Customer | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0
|  | User Manual For Admin | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0
|  | Theme Language Module | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0
|  | Test | 16 | 16 | 16 | 16 | 16 | 16 | 0 | 0
|  | Test Script | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0
|  | Prepare Data (TH EN ID) | 2 | 4 | 4 | 4 | 4 | 0 | 0 | 0
|  | Sprint backlog + Burndownchart | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0
|  | ADAPT_BP | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0
|  | Slide Present | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0
|  | Total | 48 | 40 | 32 | 24 | 16 | 8 | 0 | 0
| Member | StudenID
| Ter | 643020610-1 | นาย ธนพนธ์ รวิภาสกร
| Kate | 643020613-5 | นาย ธนากร ผาเป้า
| Jane | 643020624-0 | นางสาว ปิยาภัสร์ สติภา
| Tornia | 643021319-0 | นางสาว ทอเนีย ทะเฮรี
| Aomsin | 643021418-8 | นาย ณัฐพงษ์ แก่นกระโทก
| Kaw | 643021421-9 | นาย ธนพงษ์ เจริญพันธ์