## Sprint II Burndown Chart
SprintBurndown Chart
Sprint No | Product Backlog Items | UserStory | Initial Estimate | 2024-02-08 | 2024-02-09 | 2024-02-10 | 2024-02-11 | 2024-02-12 | 2024-02-13 | 2024-02-14
|  |  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 |  |  |  | Actual
1 | As an alumnus, I want to purchase a souvenir so that I can contribute to the College of Computing. | Design and Edit Product Page | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 |  | 1 | Jenny | 4 | Total | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
|  | Design and Edit Product Detail Page | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 |  |  |  | 4 | 86 | 86 | 86 | 86 | 74 | 50 | 0 | 0
|  | Design and Edit Cart Page | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 |  | 5 | Aomsin | 4
|  | Design and Edit Payment Page | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 |  |  |  | 4
|  | Add Module Paymant | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 |  | 3 | Ter | 6
|  | Create user manual | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 |  | 4 | Tani nya | 10
|  | Test Manual | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 |  | 4 | Tani nya | 4
|  | Add Product Shirt | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 |  | 5 | Aomsin | 4
|  | Add Product Book | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 |  | 1 | Jenny | 4
|  | Add Product Accessories | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 |  | 3 | Ter | 4
|  | Document | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 |  | 6 | Khet | 10
|  | Create Install guide | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 |  | 2 | Kaw | 4
|  | Create UAT Document | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 |  | 6 | Khet | 6
|  | Design Product | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 |  | 4 | Taniya | 2
|  | Install Prestashop | 12 | 12 | 12 | 12 | 12 | 0 | 0 | 0 |  | 2 | Kaw | 16
Remaining Effort |  |  | 86 | 86 | 86 | 86 | 74 | 50 | 0 | 0 |  |  | SumActual | 86 | Team Valocity | 86
Ideal Trend |  |  | 86 | 71.6667 | 57.3333 | 43 | 28.6667 | 14.3333 | 0 | 0 |  |  |  | Actual
2 | As a user, I want to switch language at all time. | Design Ui First page | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 | Tornia | 1 | Total | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
|  | Design Ui Second page | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Tornia | 1 | 35 | 35 | 28 | 20 | 16 | 6 | 0 | 0
|  | Design Ui Thirt page | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Tornia | 1
|  | User Manual | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | Jane | 4
|  | Theme Language Module | 6 | 6 | 6 | 6 | 6 | 0 | 0 | 0 |  | 2 | Kaw | 6
|  | Test Script | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 |  | 6 | KhetTer | 8
|  | Prepare Data (TH EN ID) | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | s | 3 | Ter Jane | 4
|  | Sprint backlog + Burndownchart | 6 | 6 | 6 | 6 | 6 | 6 | 0 | 0 |  | 5 | Aomsin | 6
|  | ADAPT_BP | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 |  | 6 | Khet | 4
Remaining Effort |  |  | 35 | 35 | 28 | 20 | 16 | 6 | 0 | 0 |  |  | SumActual | 35 | Team Valocity | 60.5
Ideal Trend |  |  | 35 | 29.1667 | 23.3333 | 17.5 | 11.6667 | 5.8333 | 0 | 0 |  |  |  | Actual
3 | As a user, I want to switch language at all time. | User Manual For Customer | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 |  | 5 | Aomsin | 2 | Total | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
|  | User Manual For Admin | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 |  | 2 | Kaw | 2 | 53 | 53 | 53 | 39 | 31 | 27 | 0 | 0
|  | Theme Language Module | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 |  |  | Kaw | 3
|  | Test | 16 | 16 | 16 | 16 | 16 | 16 | 0 | 0 |  | 3 & 6 | KhetTer | 12
|  | Test Script | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 |  |  | KhetTer | 10
|  | Prepare Data (TH EN ID) | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 |  | 4 | Tornia | 2
|  | Sprint backlog + Burndownchart | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 |  | 5 | Aomsin | 2
|  | ADAPT_BP | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 |  | 1 | Jane | 2
|  | Slide Present | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 |  | 4 | Tornia | 2
Remaining Effort |  |  | 53 | 53 | 53 | 39 | 31 | 27 | 0 | 0 |  |  | SumActual | 37 | Team Valocity | 58
Ideal Trend |  |  | 53 | 44.1667 | 35.3333 | 26.5 | 17.6667 | 8.8333 | 0 | 0
[14 empty] | Member | StudenID
[14 empty] | Ter | 643020610-1 | นาย ธนพนธ์ รวิภาสกร
[14 empty] | Kate | 643020613-5 | นาย ธนากร ผาเป้า
[14 empty] | Jane | 643020624-0 | นางสาว ปิยาภัสร์ สติภา
[14 empty] | Tornia | 643021319-0 | นางสาว ทอเนีย ทะเฮรี
[14 empty] | Aomsin | 643021418-8 | นาย ณัฐพงษ์ แก่นกระโทก
[14 empty] | Kaw | 643021421-9 | นาย ธนพงษ์ เจริญพันธ์